## Test Plan
1. About this Document
The purpose of this document is to outline the approach and methodology for conducting performance testing on the JPetStore web application
This document is prepared to give Performance Testing scope,approach, workload and data requirements with the Jpet store(Demo) web application servers.
The performance test is a testing phase to test all scenarios in scope.
The performance test should commmence only after system testing is completed and all issues are fixed
2. Test Approach
The overall approach of Performance Testing will be to ensure that the application meets the required SLA's and to baseline the current capacity of the solution and given infrastructure.
Performance testing will be performed in Production environment(Demo Application) and for real time application it will be done in QA environment
As the platform delivery to production is incremented, the performance test strategy is also to be aligned with the development model, the performance test strategy should be test early focus ensuring the defect identification
are as early as in the test cycles. The high level strategy calls out that the performance test will focus across all phases of testing for Jpet Store(Demo App)
Performance Test will be performed for every release(Not practical in Demo App but can be done in real time app) and the long term aim will be to have its execution automated through pipelines as part of the build process.
Performance test execution will be delivered in phase to support delivery.Each phase will add aditional scope to the prior phase. As part of each release, the test scripts may need to be uplifted or new scripts created inorder to
ensure the Performance test can be performed.
2.1 Execution
There will be steady ramp up of virtual users where gradually come into the system injecting load and a period of steady state where the users hold a steady load on the solution(as designed in the test) and when the stipulated test
/ desired duration is achieved , the users will gradually exit the system. During a typical test(Real time Application) in the above fashion the platform performance characteristics will be monitored using the appropriate monitoring tools.
The key focus on monitoring will be in the below area
a. Response Times and Volume Traffic
b. CPU
c. Memory
d. JVM parameters (NA to Demo App)
e. Web server stats (NA to Demo App)
f. DB stats (NA to Demo App)
To monitor the above stats access to Dynatarace or similar tool to be provided to the Performance team.
The Performance test will be executed through Non-SSO users.
The 95th percentile transaction response will be looked at meeting the SLA of 3 seconds.
Two rounds of load test for duration of 1 hr each would be performed.
2.2 Monitoring
Platform monitoring is key during the performance test execution. The performancce test team will use the same monitoring capabilities that are available in production: Splunk and Dynatrace or similar tool
2.3 Roles and Responsibilities
Role | Name | Activities
Performance Engineer | Satish Nath | Documentation
Performance Engineer | Satish Nath | Scripting & Execution
Performance Engineer | Satish Nath | Test Summary Report
3. Test Environment Details
With a highly visible and important platform in production, it is very important that the performance characteristics is well known before it is deployed into the production.
It is only possible to know all the performance characteristics of the platform and solution by mimicking the load like in the real world scenario and in an environment which is as close as possible to production
With this thought process in mind, the environment that has been provisioned for performance test is the QA environment will be replica of production environment
As this is a Demo application so we will use production environment
ENV | Application | URL
Prod | Jpet Store | https://jpetstore.aspectran.com/
4. Non-Functional Requirements
The detailed NonFunctional requirement is documented in NFR document and the transactions per day volume is extracted from NFR document.Please find the detailed NFR
Here we have Non functional requirement which we usually get from Business Analyst or from Project Team. We have to convert them the re-usable test scripts
a) In a day 12 hrs are considered to be active hrs for application 8 AM to 8 PM where the most traffic will hit the application
b) The below TPH are calculated based on the active hours of applications
Target TPH= Transactions per day/Application active hrs
233=2800/12 (TPH per each transaction per each scenario)
Target Concurrent Users= 10% of Total Users
30=10% of 300
Users per scenario= Target Concurrent Users/No of scenario
6=30/5
| Volume Per Hour to be Achieved | Concurrent Users
| 233 Pets for each pet category will be added and ordered per hour | 30
Type | Scenario Name | Total Users | No of Transactions per Scenario(A) | Volumes per Hour for each scenario(B) | Net TPH(A*B)
UI | Jpet Store Shop Fish | 6 | 9 | 233 | 2097
UI | Jpet Store Shop Dogs | 6 | 9 | 233 | 2097
UI | Jpet Store Shop Reptiles | 6 | 9 | 233 | 2097
UI | Jpet Store Shop Cats | 6 | 9 | 233 | 2097
UI | Jpet Store Shop Birds | 6 | 9 | 233 | 2097
|  |  |  | Total TPH | 10485
5. Performance Test Scope
In-Scope
1. All scenarios currently active for each category in production
2. Jpet Store platform standalone testing with identified performace test workload
3. Load Testing with current workload volume
4. Performance test all the modules listed in the workload model
5. Measurement of client side utilization and systems involved in ingesting the load
Out Of Scope
1. Paper Based Assessment(PBA)
2. Stress Testing
3. Integration Testing
4. Soak testing
5. Environment support, Stub support and activities not mentioned in In-Scope
6. Test Data Requirements
As this is a Demp App so test data has been created and by using UI services the scripts are created for testing
| Test Data Type | Count
| Non-SSO Test Users | 30
7. Types of Test
Below are the type of test that will be executed as part of Jpet store UI application
a. Load test to be run for 1 hour
b. Two rounds of load test will be executed
c. Soak test can't be run on Demo application as it might crash the application resulting blocking of client computer used for test.
d. Breakpoint test can't be run on Demo application due to above point restriction
8. Entry and Exit Criteria
8.1 Entry Criteria
a. No outstanding severity 1 or 2 defects which impact areas under Performance test
b. No functional defects with high severity are in open status
c. The test data requirements mentioned in section 6 should be functional and available to Performance test team.
d. All production level operating system and and security patches have been successfully deployed to the QA(test) environment(Not applicable in Demo App)
e. All implementation related latest code to be applied as part of the project deployment have been successfully deployed to the QA(test) environmnet(Not applicable in Demo App)
f. Deployed code is considered stable and no issues/blockers.
8.2 Exit Criteria
a. Results as documented in the phase Test Summary Report have been accepted by the project team(Technical & Business)(Applicable to Real time app)
b. All test runs are confirmed as being reliable and consistent by executing each test case twice and achieving the same result that meets the agreed measurement criteria(NFR) if applicable
c. Any defects are actioned as per the project defect management process.
8.3 Suspension Criteria
a. Unavailability of external dependent systems during execution
b. When any defect blocks further testing(Applicable to Real time app)
c. All dependencies are not met
8.4 Resumption Criteria
a. Defects that were blocking performance testing are fixed and resolved. No Blockers/showstoppers to resume performance test execution
b. These defects have been functionally verified and validated by the functional testing team
c. All pathes and defect fixes have been implemented to the QA(test) environment and is made available
8. Acceptance Criteria
Baseline needs to be defined based on phase 1 results and fine tuning application
Below are the performance counters measured with the pnv execution
Sl No | Type | Tool
1 | User Load | Jmeter
2 | Ramp up/Ramp down/Steady state | Jmeter
3 | Request volume per execution | Jmeter
4 | Error Rate | Jmeter
5 | Average Response times | Jmeter
6 | Throughput | Jmeter
7 | 90th Percentile Response times | Jmeter
8 | 95th Percentile Response times | Jmeter
9 | Web/App Server stats | Dynatrace or similar
10 | Database stats- High Cost SQLs | Dynatrace or similar
9. Client Test Machine Details
Machine OS | IP Address
Windows 11 Pro | 192.168.225.189
10. Performance Test Tools
Type | Tool
Load Test | Jmeter
Log Analysis | Splunk(NA to Demo App)
Server Monitoring | Dynatrace(NA to Demo App)
11. Documentation Scripting & Execution Timelines
The below timelines may vary as per the risk discussed in Risk sections
Task | Effort | Start | End
POC | 0.5 Day | 2024-07-10 | 2024-07-10
NFR | 0.25 Day | 2024-07-10 | 2024-07-10
Test Plan | 1 Day | 2024-07-11 | 2024-07-11
WorkLoad Model | 0.25 Day | 2024-07-12 | 2024-07-12
Scripting | 1 Day | 2024-07-12 | 2024-07-13
Load Test1 | 0.5 Day | 2024-07-14 | 2024-07-14
Load Test2 | 0.5 Day | 2024-07-14 | 2024-07-14
TSR | 1 Day | 2024-07-15 | 2024-07-16
12. Risks
a. Planned/Unplanned environment down time during Performancentesting that may occour.
b. Change in application/configuration/test data may require modification of performance test script(s). It may impact test schedules.
c. Unstable build or blocker/critical defects can affect the test schedule
d. Network bandwidth risk. Each country might have different performance experience depends on bandwidth capacity available each country and Data Centre. For WFH users, it subjects further
on individual's home network connection speed that varries from country to country.
13. Document Control
13.1 Version Control
The below document illustrates the document version control implementted in a real time project. Though the current app is a Demo app so it is not fully applicable to the process
Version | Change | Date | Author
v1.0 | Initial Draft | 2024-07-11 | Satish Nath
v1.1 | Review Comments Updated | 2024-07-12 | Performance Team
v1.2 | Walkthrough review comments updated | 2024-07-12 | Project Team
13.2 Reviewers and Approvers
The below document illustrates the document version control implementted in a real time project. Though the current app is a Demo app so it is not fully applicable to the process
Role | Name | Date | Comments
Platform Chapter Lead | James Alfred | 2024-07-13
Release Lead | Anand Sharma | 2024-07-13
Product Owner | P Vijay Kumar | 2024-07-13

## Module1
Module Name: Shop Pet Fish
1. Test Objectives
Below objectives are measured to check the consistency and performance during tests.
a. Certify that the Jpet Store services from different source are responding within the defined response time mentioned in Work Load Model
b. Certify that the Jpet Store Fish section is able to handle volume of 2097 requests from all source systems to Jpet Store Platform
c. results will be compared against the Baseline established in 1st Load Test
d. All transactions 95th percentile response time should meet the SLA of 3 seconds
Jpet Store Server Utilization limits:
Server Type | CPU Utilization | Memory Utilization | Disk Utilization
Client Computer | Average should be below 80%.Spikes(>90%) should not extend beyond 2 mins | System memory expected to be below 80% | Average should be below 80%
App Server(NA)
JVM Parameter(NA)
Database(NA)
2. Test Machine Details
Server Type | OS | Server Name | IP Address | Configuration
NA | Windows | Acer Nitro5 AN515 | 192.168.225.189 | vCPU: 4, RAM:8 GB, C Drive: 236 GB(SSD), D Drive: 1TB
3. Test Data and Parameters
As this is a Demo App which requires the User name as Test Data
User Name | Password
Fish1 | 1234
Fish2 | 1234
Fish3 | 1234
Fish4 | 1234
Fish5 | 1234
Fish6 | 1234
4. Test Execution Steps
Step1: Launch Jpet Store Application
Step2: Click Sign In
Step3: Click on Fish
Step4: Select any Fish and Click on respective Product ID
Step5: In Shopping Cart screen select any Item ID and click on respective Add to Cart button
Step6: Update quantity and select proceed to checkout
Step7: Enter Payment details, billing address and click continue
Step8: Check details and click confirm
Step9: Click SignOut
5. Expected Results
The expectation is the Jpet Store application should able to sustain the expected number of vusers and achieve the expected TPH volume
6. Performance Metrics
All the business transaction 95th percentile response time should be below 3 sec's and able to achieve TPH of 2097
The error rate should be below 2%

## Module2
Module Name: Shop Pet Dogs
1. Test Objectives
Below objectives are measured to check the consistency and performance during tests.
a. Certify that the Jpet Store services from different source are responding within the defined response time mentioned in Work Load Model
b. Certify that the Jpet Store Dogs section is able to handle volume of 2097 requests from all source systems to Jpet Store Platform
c. results will be compared against the Baseline established in 1st Load Test
d. All transactions 95th percentile response time should meet the SLA of 3 seconds
Jpet Store Server Utilization limits:
Server Type | CPU Utilization | Memory Utilization | Disk Utilization
Client Computer | Average should be below 80%.Spikes(>90%) should not extend beyond 2 mins | System memory expected to be below 80% | Average should be below 80%
App Server(NA)
JVM Parameter(NA)
Database(NA)
2. Test Machine Details
Server Type | OS | Server Name | IP Address | Configuration
NA | Windows | Acer Nitro5 AN515 | 192.168.225.189 | vCPU: 4, RAM:8 GB, C Drive: 236 GB(SSD), D Drive: 1TB
3. Test Data and Parameters
As this is a Demo App which requires the User name as Test Data
User Name | Password
Dog1 | 1234
Dog2 | 1234
Dog3 | 1234
Dog4 | 1234
Dog5 | 1234
Dog6 | 1234
4. Test Execution Steps
Step1: Launch Jpet Store Application
Step2: Click Sign In
Step3: Click on Dogs
Step4: Select any Dog and Click on respective Product ID
Step5: In Shopping Cart screen select any Item ID and click on respective Add to Cart button
Step6: Update quantity and select proceed to checkout
Step7: Enter Payment details, billing address and click continue
Step8: Check details and click confirm
Step9: Click SignOut
5. Expected Results
The expectation is the Jpet Store application should able to sustain the expected number of vusers and achieve the expected TPH volume
6. Performance Metrics
All the business transaction 95th percentile response time should be below 3 sec's and able to achieve TPH of 2097
The error rate should be below 2%

## Module3
Module Name: Shop Pet Reptiles
1. Test Objectives
Below objectives are measured to check the consistency and performance during tests.
a. Certify that the Jpet Store services from different source are responding within the defined response time mentioned in Work Load Model
b. Certify that the Jpet Store Reptiles section is able to handle volume of 2097 requests from all source systems to Jpet Store Platform
c. results will be compared against the Baseline established in 1st Load Test
d. All transactions 95th percentile response time should meet the SLA of 3 seconds
Jpet Store Server Utilization limits:
Server Type | CPU Utilization | Memory Utilization | Disk Utilization
Client Computer | Average should be below 80%.Spikes(>90%) should not extend beyond 2 mins | System memory expected to be below 80% | Average should be below 80%
App Server(NA)
JVM Parameter(NA)
Database(NA)
2. Test Machine Details
Server Type | OS | Server Name | IP Address | Configuration
NA | Windows | Acer Nitro5 AN515 | 192.168.225.189 | vCPU: 4, RAM:8 GB, C Drive: 236 GB(SSD), D Drive: 1TB
3. Test Data and Parameters
As this is a Demo App which requires the User name as Test Data
User Name | Password
Reptile1 | 1234
Reptile2 | 1234
Reptile3 | 1234
Reptile4 | 1234
Reptile5 | 1234
Reptile6 | 1234
4. Test Execution Steps
Step1: Launch Jpet Store Application
Step2: Click Sign In
Step3: Click on Reptiles
Step4: Select any Reptile and Click on respective Product ID
Step5: In Shopping Cart screen select any Item ID and click on respective Add to Cart button
Step6: Update quantity and select proceed to checkout
Step7: Enter Payment details, billing address and click continue
Step8: Check details and click confirm
Step9: Click SignOut
5. Expected Results
The expectation is the Jpet Store application should able to sustain the expected number of vusers and achieve the expected TPH volume
6. Performance Metrics
All the business transaction 95th percentile response time should be below 3 sec's and able to achieve TPH of 2097
The error rate should be below 2%

## Module4
Module Name: Shop Pet Cats
1. Test Objectives
Below objectives are measured to check the consistency and performance during tests.
a. Certify that the Jpet Store services from different source are responding within the defined response time mentioned in Work Load Model
b. Certify that the Jpet Store Cats section is able to handle volume of 2097 requests per hour from all source systems to Jpet Store Platform
c. results will be compared against the Baseline established in 1st Load Test
d. All transactions 95th percentile response time should meet the SLA of 3 seconds
Jpet Store Server Utilization limits:
Server Type | CPU Utilization | Memory Utilization | Disk Utilization
Client Computer | Average should be below 80%.Spikes(>90%) should not extend beyond 2 mins | System memory expected to be below 80% | Average should be below 80%
App Server(NA)
JVM Parameter(NA)
Database(NA)
2. Test Machine Details
Server Type | OS | Server Name | IP Address | Configuration
NA | Windows | Acer Nitro5 AN515 | 192.168.225.189 | vCPU: 4, RAM:8 GB, C Drive: 236 GB(SSD), D Drive: 1TB
3. Test Data and Parameters
As this is a Demo App which requires the User name as Test Data
User Name | Password
Cat1 | 1234
Cat2 | 1234
Cat3 | 1234
Cat4 | 1234
Cat5 | 1234
Cat6 | 1234
4. Test Execution Steps
Step1: Launch Jpet Store Application
Step2: Click Sign In
Step3: Click on Cats
Step4: Select any Cat and Click on respective Product ID
Step5: In Shopping Cart screen select any Item ID and click on respective Add to Cart button
Step6: Update quantity and select proceed to checkout
Step7: Enter Payment details, billing address and click continue
Step8: Check details and click confirm
Step9: Click SignOut
5. Expected Results
The expectation is the Jpet Store application should able to sustain the expected number of vusers and achieve the expected TPH volume
6. Performance Metrics
All the business transaction 95th percentile response time should be below 3 sec's and able to achieve TPH of 2097
The error rate should be below 2%

## Module5
Module Name: Shop Pet Birds
1. Test Objectives
Below objectives are measured to check the consistency and performance during tests.
a. Certify that the Jpet Store services from different source are responding within the defined response time mentioned in Work Load Model
b. Certify that the Jpet Store Birds section is able to handle volume of 2097 requests per hour from all source systems to Jpet Store Platform
c. results will be compared against the Baseline established in 1st Load Test
d. All transactions 95th percentile response time should meet the SLA of 3 seconds
Jpet Store Server Utilization limits:
Server Type | CPU Utilization | Memory Utilization | Disk Utilization
Client Computer | Average should be below 80%.Spikes(>90%) should not extend beyond 2 mins | System memory expected to be below 80% | Average should be below 80%
App Server(NA)
JVM Parameter(NA)
Database(NA)
2. Test Machine Details
Server Type | OS | Server Name | IP Address | Configuration
NA | Windows | Acer Nitro5 AN515 | 192.168.225.189 | vCPU: 4, RAM:8 GB, C Drive: 256 GB(SSD), D Drive: 1TB
3. Test Data and Parameters
As this is a Demo App which requires the User name as Test Data
User Name | Password
Bird1 | 1234
Bird2 | 1234
Bird3 | 1234
Bird4 | 1234
Bird5 | 1234
Bird6 | 1234
4. Test Execution Steps
Step1: Launch Jpet Store Application
Step2: Click Sign In
Step3: Click on Birds
Step4: Select any Bird and Click on respective Product ID
Step5: In Shopping Cart screen select any Item ID and click on respective Add to Cart button
Step6: Update quantity and select proceed to checkout
Step7: Enter Payment details, billing address and click continue
Step8: Check details and click confirm
Step9: Click SignOut
5. Expected Results
The expectation is the Jpet Store application should able to sustain the expected number of vusers and achieve the expected TPH volume
6. Performance Metrics
All the business transaction 95th percentile response time should be below 3 sec's and able to achieve TPH of 2097
The error rate should be below 2%